## Slide 1
ALPHA MANUFACTURING GROUP
ERP Transformation Program
Prepared for: AMG Executive Team & Board of Directors
May 2026

## Slide 2
What is Enterprise Resource Planning (ERP)?
Enterprise Resource Planning (ERP) is a type of software system that helps organizations manage and integrate their core business processes in one central platform. It allows departments such as finance, human resources, inventory, sales, procurement, and customer service to share data and work together efficiently. Some Benefits include;
Improves Efficiency
Streamlines operations and automates routine tasks.
Centralizes Data
Provides a single source of truth for all business information.
Enhances Communication
Fosters seamless information exchange across departments.
Supports Better Decision-Making
Offers real-time insights for informed strategic choices.
Increases Productivity
Empowers employees to focus on value-added activities.
Improves Customer Service
Enables faster responses and personalized interactions.
Strengthens Security
Protects sensitive data with robust access controls.
Supports Business Growth
Scales with your organization and facilitates expansion.

## Slide 3
What Happens When ERP Programs Go Wrong
Program
Cost Reality
Outcome
Lesson Learnt
UK NHS — Lorenzo EHR
Planned: £6.4B → Actual: £10B
Cancelled 2011. Limited results delivered.
Scale amplifies mistakes; integration issues sink large programmes.
Canada Phoenix Pay — Oracle
Cost: $3.5B CAD and rising
Still not live. 80% of employees had payroll errors.
Payroll modernisation requires meticulous testing; errors destroy trust.
U.S. Virtual Fence — Boeing
Cost: $1.4B for just 23 miles
Cancelled. Technology did not match operational reality.
Technology must match the real-world environment it operates in.
Queensland Health — SAP/IBM
Planned: $6M AUD → Actual: $1.2B AUD
Employees unpaid. Australia's worst IT investment.
Excessive customisation and weak governance are a recipe for failure.
U.S. Air Force — Oracle/CSC
Cost: $1B+ over 7 years
Never went live. Goal was to merge 240 systems into one.
Unrealistic scope and no vendor accountability guarantee failure.

## Slide 4
Six Common Threads Behind Every Failure
1
Politically Driven Procurement
Well-intentioned but flawed vendor selection processes introduce risk from Day 1. Decisions made for the wrong reasons.
2
Inadequate Requirements Gathering
Without thorough requirements gathering, project expectations are never clearly defined and cannot be met.
3
Weak Governance
Without strong oversight and a clear decision-making authority, scope and costs spiral out of control.
4
Inadequate Change Management
Technology adoption is a human challenge first. People resist change without structured support and communication.
5
Unrealistic Budgets & Timelines
Overpromising at the start leads to underdelivering later. Pressure to start leads to shortcuts that cause failures.
6
No Vendor Accountability
Open-chequebook relationships with suppliers rarely end well. Contracts must define deliverables and consequences.

## Slide 5
Why AMG Must Act Now
Margin Erosion
80% of custom orders experience margin erosion. No reliable contribution margin view per job exists. Engineering complexity and BOM errors go undetected until it's too late to act.
Operational Risk
The nightly BOM sync between the legacy ERP and Engineering database fails regularly, causing manufacturing delays, rework, material waste, and missed customer ship dates.
Blind Reporting
Finance operates on Excel extracts from a 20-year-old system. Labor tracking is unreliable. Leadership cannot see job profitability and cannot close books with confidence.
The Board has mandated a 12-month go-live. The cost of inaction exceeds the cost of transformation.

## Slide 6
Where AMG Is vs. Where It Needs to Be
Where AMG Is Today
Manual, complex 'unique' processes riddled with inefficiencies
Disparate applications hindering reporting, insights and analytics
Limited data model and poor master data governance
Task-focused workforce with limited digital capabilities
Fragile BOM sync causing manufacturing delays and margin erosion
Where AMG Needs to Be
Standardised, end-to-end processes enabling efficiency and scale
Unified platform with real-time reporting and margin visibility
Strong data governance anchored to a single source of truth
Digitally capable workforce driving innovation and value
Integrated Engineering and ERP eliminating BOM errors from Day 1

## Slide 7
Three Non-Negotiable Principles Guiding Every Decision
Operational Continuity First
No disruption to order fulfilment, customer commitments, or monthly financial close. Every scope and timing decision is evaluated against this principle first. Cutover only happens after parallel runs confirm full parity with the legacy system.
Margin Recovery as the North Star
The entire program exists to stop 80% of orders losing money. Every module selected for Day-1 go-live must contribute directly to contribution margin visibility. Job costing is not optional — it is the primary deliverable of the transformation.
Scope Discipline Above All Else
Fewer than 15 customisations at go-live. Every scope addition must pass a three-question test: Is it required for Day-1 operations? Does a standard configuration exist? What is the ongoing maintenance cost? The Steering Committee holds veto power.

## Slide 8
Four-Phase Delivery Roadmap
Phase 0 · Foundation
M1–2
Vendor selection & contracting
BOM audit & data cleanse
Project governance established
Parallel reporting layer live
Change management plan developed
Phase 1 · Core Go-Live
M3–12
Finance + multi-entity consolidation
Unified Engineering / BOM
Manufacturing execution & MRP
Project / job costing
Procurement & multi-location inventory
Phase 2 · Stabilise
M12–15
Hypercare & issue resolution
KPI dashboard validation
User adoption measurement
CRM integration scoping
Process improvement cycle
Phase 3 · Extend
M15+
CRM integration
HRIS / Payroll migration
Advanced analytics & BI
EDI & customer portal
Continuous improvement
✓ Target Go-Live: Month 12

## Slide 9
Top 5 Program Risks & Mitigations
Risk
Description
Severity
Mitigation
R1
BOM data quality — inaccurate BOMs corrupt the new system from Day 1
HIGH
Mandatory BOM audit in Phase 0; Engineering sign-off required; BOM freeze during cutover window
R2
Scope creep — departmental wish lists push the timeline beyond 12 months
HIGH
Exec Steering Committee veto power; formal change control; CFO + COO approval for all additions
R3
Key-person dependency — 3–4 people hold all institutional ERP knowledge
MED
Structured knowledge transfer in Phase 0; shadow training programme; strong vendor hypercare SLA
R4
Cutover integration failure — data loss during the dual-system transition period
HIGH
Parallel run for 2+ pay periods and 1 full month-end close before legacy decommission
R5
User adoption failure — teams revert to Excel workarounds after go-live
MED
Change management starts Month 1; role-based training; super-user network at all 5 locations

## Slide 10
Day-1 Scope: What's In vs. Deliberately Out
✓ Day-1 Must-Haves
Financial Accounting & Multi-Entity Consolidation (US + Canada)
Unified Engineering / BOM Management — eliminates the broken nightly sync
Manufacturing Execution & MRP — work orders, shop floor, labour actuals
Procurement & Multi-Location Inventory Management
Project / Job Costing — the primary tool for margin recovery
→ Deliberately Deferred
CRM Integration
Cloud CRM continues standalone; integrated in Phase 3
HRIS / Payroll Migration
Zero-tolerance disruption area; migrate only after core ERP is stable
Advanced BI & Analytics
Base KPI reporting live Day 1; full analytics suite deferred to Phase 3
EDI & Customer Portal
Manual processes continue through the stabilisation period
Full Historical Data (7+ yrs)
7+ year archive stays in legacy read-only; 2–3 years migrated

## Slide 11
Implementation Methodology: Vision to Evolve
Vision
Define transformation vision & objectives
Project kick-off and mobilisation
Conduct workshops to validate business requirements
Develop change management plan
Provision ERP instances
Validate
Conduct gap analysis
Develop final solution architecture
Solution review and sign-off
Conduct CRP1
Review and sign-off requirements
Construct & Test
Configure applications for UAT
Build data migration plan
Develop training manuals
Conduct end-user training
Prepare functional & technical specs
Deploy
Execute full data migration
Conduct UAT and sign-off
Deploy cutover production plan
Establish change management tools
Go-live readiness checks + Go-Live
Evolve
Post go-live hypercare support
Establish continuous improvement
Transition to managed service
KPI validation & reporting
User adoption measurement
Each phase has formal sign-off gates. No phase begins until the prior phase deliverables are reviewed, approved, and baselined.

## Slide 12
Data Migration Strategy — Not Everything Needs to Move
Phase 0 · M1–2
Parallel reporting layer live
Data audit & cleanse begins
Legacy = system of record
Phase 1 · M3–12
Dual-entry window (2 weeks)
Parallel month-end close runs
Active data migrated to new ERP
Go-Live · M12
New ERP = system of record
Legacy read-only for 6 months
KPI dashboard live from Day 1
Phase 3 · M15+
Legacy fully archived
Full analytics suite live
Complete decommission of legacy
DATA CATEGORY
MIGRATION APPROACH
Open Sales Orders & Active BOMs
Full migration; manually validated by Engineering & Sales before cutover
Open Purchase Orders & Commitments
Full migration; Procurement team validates all open POs before cutover
GL Balances at Period-End Cutover
Period-end balances migrated; full GL history stays in legacy (read-only)
2–3 Years Transactional History
Migrated to new ERP or parallel data warehouse for operational queries
7+ Year Statutory Archive
Retained in read-only legacy or immutable archive — no migration required

## Slide 13
Month-End Close Protection Plan
Cutover Timing
Go-live targets the first business day of a month — never mid-month. This ensures Finance has a clean period-end baseline with no transactions split across two systems.
Parallel Close
Full month-end close runs in both systems simultaneously for the first post-go-live period. Finance must reconcile to within $1,000 variance before signing off on the new system.
Finance Hypercare
ERP vendor finance specialists are embedded on-site for the first two close cycles. Vendor SLA guarantees a 2-hour response time during close week.
Rollback Trigger
Pre-defined criteria: if month-end close cannot be completed within 5 business days post-cutover, the program automatically reverts to the legacy system until the issue is resolved.

## Slide 14
ALPHA MANUFACTURING GROUP
Recommended Next Steps
Week 1
Appoint Program Sponsor (C-suite), Project Manager & Executive Steering Committee
Weeks 2–4
Issue RFP to 3–5 cloud ERP vendors with AMG's engineer-to-order requirements included
Month 2
Select vendor; begin Phase 0 BOM audit, data cleanse, and change management planning
Month 3
Program kick-off; immediately freeze new customisations on the legacy system
Board approval authorises commencement of Phase 0. The cost of inaction far exceeds the cost of transformation.